## Functional
Project Name: | Emergency Expert
Superviser Name: | Dr. Ali Afzal
Deliverable: | Project Status
ID | Functional Requirement | Priority | Status Completed | Deadline (week no of semester) | Resource
1 | Patient can signup | High | 100% | N/A | Saad Shafiq, Anam Qaiser
2 | Patient can login/logout | High | 100% | N/A | Saad Shafiq, Anam Qaiser
3 | Patient is able to edit his profile | High | 100% | N/A | Saad Shafiq, Anam Qaiser
4 | Patient can view information of a specific doctor | High | 100% | N/A | Saad Shafiq, Anam Qaiser
5 | Patient can search for a specific doctor | High | 100% | N/A | Saad Shafiq, Anam Qaiser
6 | Patient is able to add an item to cart | High | 100% | N/A | Saad Shafiq, Anam Qaiser
7 | Patient is able to remove item from cart | High | 100% | N/A | Saad Shafiq, Anam Qaiser
8 | Patient can place order | High | 100% | N/A | Saad Shafiq, Anam Qaiser
9 | Patient can cancel his order within 2 minutes | High | 100% | N/A | Saad Shafiq, Anam Qaiser
10 | Patient can choose from the given payment options | High | 100% | N/A | Saad Shafiq, Anam Qaiser
11 | Patient can track his order | Medium | 100% | N/A | Saad Shafiq, Anam Qaiser
12 | Patient can receive support | Low | 100% | N/A | Saad Shafiq, Anam Qaiser
13 | Patient can rate and/or write a review for the doctor | Low | 100% | N/A | Saad Shafiq, Anam Qaiser
14 | Patient is able to view the recommendations | High | 100% | N/A | Saad Shafiq, Anam Qaiser
15 | Doctor can sign up with the organization | High | 40% | Week 6 | Abdul Rehman, Saad Shafiq
16 | Doctor can login/logout | High | 40% | Week 6 | Abdul Rehman, Saad Shafiq
17 | Doctor can edit his profile (except rating) | Low | 40% | Week 6 | Abdul Rehman, Saad Shafiq
18 | Doctor can accept instant, weekly and/or monthly appointments | High | 70% | Week 6 | Abdul Rehman, Saad Shafiq
19 | Pharmacist is able to add an item to his menu | High | 50% | Week 8 | Abdul Rehman, Anam Qaiser
20 | Pharmacist can edit item details | High | 30% | Week 8 | Abdul Rehman, Anam Qaiser
21 | Pharmacist can remove an item from his menu | High | 80% | Week 8 | Abdul Rehman, Anam Qaiser
22 | Pharmacist can register himself with the organization | Low | 60% | Week 8 | Abdul Rehman, Anam Qaiser
23 | Pharmacist can login/logout | High | 50% | Week 8 | Abdul Rehman, Anam Qaiser
24 | Pharmacist can receive orders | High | 70% | Week 8 | Abdul Rehman, Anam Qaiser
25 | Pharmacist can view his points | Medium | 70% | Week 8 | Abdul Rehman, Anam Qaiser
26 | Pharmacist can update delivery status | High | 70% | Week 8 | Abdul Rehman, Anam Qaiser
27 | Admin can login/logout | High | 70% | Week 10 | Abdul Rehman, Saad Shafiq
28 | Admin can add a Hospital | Low | 30% | Week 10 | Abdul Rehman, Saad Shafiq
29 | Admin can add and/or delete a Hospital | Low | 70% | Week 10 | Abdul Rehman, Saad Shafiq
30 | Admin is able to provide customer support to the Patient | Low | 40% | Week 10 | Abdul Rehman, Saad Shafiq

## Non-Functional
Project Name: | Emergency Expert
Superviser Name: | Dr. Ali Afzal
Deliverable: | Project Status
ID | Non-Functional Requirement | Priority | Status Completed | Deadline (week no of semester) | Resource
1 | Reusability - The system must be easy for new users to use | High | 100% | N/A | Abdul Rehman, Anam Qaiser, Saad Shafiq
2 | Performance - Ten thousand members will be able to access the system at a given time | Low | 40% | Week 8 | Abdul Rehman, Anam Qaiser, Saad Shafiq
3 | Extensibility - There will be separate platforms for each actor | High | 100% | N/A | Abdul Rehman, Anam Qaiser, Saad Shafiq
4 | Security - The system must protect the private data of each actor | Medium | 60% | Week 12 | Abdul Rehman, Anam Qaiser, Saad Shafiq
5 | Supportability - There will be separate android applications for each actor, as well as a website for clients. | High | 70% | Week 13 | Abdul Rehman, Anam Qaiser, Saad Shafiq
6 | Reliability - Portal will be active 24 hours a day, but there might be delay between 1 am to 6 am | Medium | 40% | Week 13 | Abdul Rehman, Anam Qaiser, Saad Shafiq

## Instructions
Instructions For Completing This Document
Complete the Project Name and Superviser Name
ID: A unique ID number used to identify the requirement
Functional Requirement: This column should be populated with a description of the functional requirement. | Non-Functional Requirement: This column should be populated with a description of the non-functional requirement.
Status: This column should be populated with the current status of the functional requirement.
Deadline: This column should be populated for the requirements whose status is incomplete.
Resource: Team member who completed/will complete the requirement implmentation.